## Sheet1 (hidden)
Row Labels | Count of Description
Fttx-Customer cancelled-Not applied | 7
Fttx-Customer no show | 10
Fttx-Customer postponed installation | 12
Fttx-No free port-inactive drop cable | 1
Fttx-Pending service activation issue | 1
Fttx-Re-Migration | 3
Fttx-Sharing villa-IDP access issue | 7
Fttx-Technical issue-Customer side | 15
Fttx-Technical issue-ooredoo | 10
Fttx-Wrong Electricty number | 4
Fttx-Wrong splitter | 8
Successful Installation | 61
(blank)
Grand Total | 139

## Sheet2 (hidden)
Row Labels | Count of Description
Total Work order | 139
Completed | 61
Fttx-Customer cancelled-Not applied | 7
Fttx-Customer no show | 10
Fttx-Customer postponed installation | 12
Fttx-No free port-inactive drop cable | 1
Fttx-Pending service activation issue | 1
Fttx-Re-Migration | 3
Fttx-Sharing villa-IDP access issue | 7
Fttx-Technical issue-Customer side | 15
Fttx-Technical issue-ooredoo | 10
Fttx-Wrong Electricty number | 4
Fttx-Wrong splitter | 8

## Sheet3 (hidden)
Row Labels | Count of Description
Fttx-Customer cancelled-Not applied | 3
Fttx-Customer no show | 9
Fttx-Customer postponed installation | 11
Fttx-Pending service activation issue | 3
Fttx-Re-Migration | 5
Fttx-Sharing villa-IDP access issue | 9
Fttx-Splitter not installed | 1
Fttx-Technical issue-Customer side | 23
Fttx-Technical issue-ooredoo | 10
Fttx-Wrong Electricty number | 1
Fttx-Wrong splitter | 2
Successful Installation | 66
(blank)
Grand Total | 143

## Sheet4 (hidden)
Total W.O | 143
Completed | 66
Fttx-Customer cancelled-Not applied | 3
Fttx-Customer no show | 9
Fttx-Customer postponed installation | 11
Fttx-Pending service activation issue | 3
Fttx-Re-Migration | 5
Fttx-Sharing villa-IDP access issue | 9
Fttx-Splitter not installed | 1
Fttx-Technical issue-Customer side | 23
Fttx-Technical issue-ooredoo | 10
Fttx-Wrong Electricty number | 1
Fttx-Wrong splitter | 2

## Sheet5 (hidden)
Row Labels | Count of Description
Fttx-Customer cancelled-Not applied | 5
Fttx-Customer no show | 10
Fttx-Customer postponed installation | 7
Fttx-Re-Migration | 2
Fttx-Sharing villa-IDP access issue | 8
Fttx-Splitter not installed | 2
Fttx-Technical issue-Customer side | 18
Fttx-Technical issue-ooredoo | 10
Fttx-Wrong Electricty number | 4
Fttx-Wrong splitter | 5
Successful Installation | 68
(blank)
Grand Total | 139

## Sheet6 (hidden)
Row Labels | Count of Description
Fttx-Customer cancelled-Not applied | 2
Fttx-Customer no show | 12
Fttx-Customer postponed installation | 11
Fttx-Re-Migration | 2
Fttx-Sharing villa-IDP access issue | 9
Fttx-Technical issue-Customer side | 28
Fttx-Technical issue-ooredoo | 10
Fttx-Wrong Electricty number | 1
Fttx-Wrong splitter | 4
Successful Installation | 62
(blank)
Grand Total | 141

## Sheet7 (hidden)
Row Labels | Count of Description
Fttx-Block wiring required-New building | 1
Fttx-Customer cancelled-Not applied | 3
Fttx-Customer no show | 10
Fttx-Customer postponed installation | 11
Fttx-No free port-inactive drop cable | 1
Fttx-Pending service activation issue | 1
Fttx-Re-Migration | 3
Fttx-Sharing villa-IDP access issue | 3
Fttx-Splitter not installed | 1
Fttx-Technical issue-Customer side | 20
Fttx-Technical issue-ooredoo | 8
Fttx-Wrong Electricty number | 1
Fttx-Wrong service information. | 1
Fttx-Wrong splitter | 6
Successful Installation | 67
(blank)
Grand Total | 137

## Sheet11 (hidden)
Row Labels | Count of Description
Fttx-Block wiring required-New building | 1
Fttx-Customer no show | 13
Fttx-Customer postponed installation | 8
Fttx-Re-Migration | 8
Fttx-Sharing villa-IDP access issue | 8
Fttx-Splitter not installed | 1
Fttx-Technical issue-Customer side | 25
Fttx-Technical issue-ooredoo | 15
Fttx-Wrong Electricty number | 2
Fttx-Wrong splitter | 7
Successful Installation | 63
(blank)
Grand Total | 151

## Sheet8 (hidden)
Row Labels | Count of Description
Fttx-Customer cancelled-Not applied | 5
Fttx-Customer no show | 11
Fttx-Customer postponed installation | 8
Fttx-Re-Migration | 3
Fttx-Sharing villa-IDP access issue | 7
Fttx-Technical issue-Customer side | 29
Fttx-Technical issue-ooredoo | 9
Fttx-Wrong Electricty number | 1
Fttx-Wrong service information | 1
Fttx-Wrong splitter | 3
Successful Installation | 71
(blank)
Grand Total | 148

## Count of description
Row Labels | Count of Description
FTTX - Customer Cancelled/Not applied | 7
FTTX - CUSTOMER NOT REACHABLE | 5
FTTX - CUSTOMER POSTPONED INSTALLATION | 12
FTTX - Pending due to service activation issues | 1
FTTX - RE-MIGRATION | 1
FTTX - Sharing Villa IDP Access issue | 1
FTTX - Splitter not installed | 2
FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | 6
FTTX - TECHNICAL ISSUE Ooredoo | 4
FTTX – Wrong Electricity Number | 1
Successful Installation | 99
Grand Total | 139

## count of type
Row Labels | Count of Type
Copper | 1
migration | 10
Modified | 68
NewAcquisition | 59
WLL | 1
Grand Total | 139

## Count of remarks
Row Labels | Count of Remarks
Completed | 99
Pending | 40
Grand Total | 139

## count of residential
Count of Segment | Column Labels | [5 empty] | c
Row Labels | Copper | migration | Modified | NewAcquisition | WLL | Grand Total
Business | 1 | 1 | 5 | 7 |  | 14
Business Residential |  |  | 1 | 3 |  | 4
Residential |  | 9 | 62 | 49 | 1 | 121
Grand Total | 1 | 10 | 68 | 59 | 1 | 139

## Overall
sn | Supplier Name | Appointment Date | Type | WO No. | Electricity No. | Site ID | Installation Scenario | Segment | Remarks | Description | Additional Description
1 | INTER-TECH | 2019-10-07 | Modified | 113569087 | 1041994 | BIM/8/S1503 | B2H | Residential | Completed | Successful Installation
2 | INTER-TECH | 2019-10-07 | Modified | 114752500 | - | BIM/11/S1287 | B2H | Business Residential | Completed | Successful Installation
3 | INTER-TECH | 2019-10-07 | Modified | 114660927 | 198478 | BIM/18/S4508 | B2H | Residential | Completed | Successful Installation
4 | INTER-TECH | 2019-10-07 | Modified | 115068075 | 1100896 | BIM/14/S2423 | B2H | Residential | Completed | Successful Installation
5 | INTER-TECH | 2019-10-07 | Modified | 115091103 | 130841 | BIM/2/S2399 | B2H | Residential | Completed | Successful Installation
6 | INTER-TECH | 2019-10-07 | Modified | 114170207 | 1017099 | BIM/6/S0636 | B2H | Residential | Completed | Successful Installation
7 | INTER-TECH | 2019-10-07 | Modified | 115041362 | 1156097 | KRC/4/S0359 | UG | Residential | Completed | Successful Installation
8 | INTER-TECH | 2019-10-07 | Modified | 115103531 | 88226 | DFS/6/S1607 | B2H | Business | Completed | Successful Installation
9 | INTER-TECH | 2019-10-07 | NewAcquisition | 114842431 | 1285777 | LSL/17/S2841 | B2H | Residential | Completed | Successful Installation
10 | INTER-TECH | 2019-10-07 | NewAcquisition | 114871916 | 149123 | WBK/1/S0056 | UG | Business | Completed | Successful Installation
11 | INTER-TECH | 2019-10-07 | NewAcquisition | 112246798 | 1291196 | LSL/16/S3006 | B2H | Business | Completed | Successful Installation
12 | INTER-TECH | 2019-10-07 | NewAcquisition | 113328984 | 1258047 | USA/8/S1056 | UG | Residential | Completed | Successful Installation
13 | INTER-TECH | 2019-10-07 | migration | 94752562 | 125113 | WBY/1/S0023 | UG | Residential | Completed | Successful Installation
14 | INTER-TECH | 2019-10-07 | NewAcquisition | 115004532 | 147462 | MKD/4/S0858 | UG | Residential | Completed | Successful Installation
15 | INTER-TECH | 2019-10-07 | migration | 114243742 | 72593 | WBC/1/S0357 | UG | Residential | Completed | Successful Installation
16 | INTER-TECH | 2019-10-07 | NewAcquisition | 114761537 | 1285758 | LSL/17/S2839 | B2H | Residential | Completed | Successful Installation
17 | INTER-TECH | 2019-10-07 | Modified | 115107789 | 45362 | KMN/1/S0075 | OH | Residential | Completed | Successful Installation | OLD TID : 114663620
18 | INTER-TECH | 2019-10-07 | NewAcquisition | 114776246 | 1357812 | KAE/1/S0010 | UG | Residential | Completed | Successful Installation
19 | INTER-TECH | 2019-10-07 | NewAcquisition | 106039346 | 1355978 | USM/6/S1073 | UG | Residential | Completed | Successful Installation
20 | INTER-TECH | 2019-10-07 | NewAcquisition | 114604609 | 1002340 | WBS/2/S0203 | B2H | Residential | Completed | Successful Installation
21 | INTER-TECH | 2019-10-07 | NewAcquisition | 114245418 | - | WBS/4/S1272 | B2H | Business Residential | Completed | Successful Installation
22 | INTER-TECH | 2019-10-07 | NewAcquisition | 115077466 | 1208568 | KRC/4/S0449 | UG | Residential | Completed | Successful Installation
23 | INTER-TECH | 2019-10-07 | NewAcquisition | 113275008 | 1246587 | WBL/3/S0169 | UG | Residential | Completed | Successful Installation
24 | INTER-TECH | 2019-10-07 | NewAcquisition | 113526410 | 1208568 | KRC/4/S0449 | UG | Residential | Completed | Successful Installation
25 | INTER-TECH | 2019-10-07 | NewAcquisition | 115058017 | 1357374 | KSM/2/S0329 | UG | Residential | Completed | Successful Installation
26 | INTER-TECH | 2019-10-07 | Modified | 115105388 | 130799 | BIM/2/S4397 | B2H | Business | Completed | Successful Installation
27 | INTER-TECH | 2019-10-07 | migration | 113261535 | 102093 | NJC-20-M254-1 | MDU | Residential | Completed | Successful Installation
28 | INTER-TECH | 2019-10-07 | NewAcquisition | 114223324 | 123572 | RAS/6/S0764/4 | B2H | Residential | Completed | Successful Installation
29 | INTER-TECH | 2019-10-07 | Modified | 114890792 | 1140298 | DME/8/S1288/0 | B2H | Residential | Completed | Successful Installation
30 | INTER-TECH | 2019-10-07 | NewAcquisition | 114243618 | 1248318 | WUK/15/S3021/5 | B2H | Residential | Completed | Successful Installation
31 | INTER-TECH | 2019-10-07 | Modified | 115094998 | 1344267 | WUK/11/S1627/7 | UG | Residential | Completed | Successful Installation | Old TR/113596130
32 | INTER-TECH | 2019-10-07 | NewAcquisition | 115060213 | 1141911 | WUK/1/S0424/1 | UG | Residential | Completed | Successful Installation | Old TR/115000704
33 | INTER-TECH | 2019-10-07 | Modified | 115051420 | Q-120788 | MKD/6/S0799/12 | B2H | Residential | Completed | Successful Installation | Old TR/114240949
34 | INTER-TECH | 2019-10-07 | Modified | 115092322 | 12018 | NJC/17/S2182/13 | OH | Residential | Completed | Successful Installation | Old TR/114997999
35 | INTER-TECH | 2019-10-07 | NewAcquisition | 115087188 | 148250 | MKD/2/S0818/12 | UG | Residential | Completed | Successful Installation | Old TR/114851539
36 | INTER-TECH | 2019-10-07 | Modified | 112852739 | 1130251 | IME/4/S0421/1 | UG | Residential | Completed | Successful Installation
37 | INTER-TECH | 2019-10-07 | NewAcquisition | 115106620 | 157412 | IAK/1/S0422/8 | B2H | Residential | Completed | Successful Installation | Old TR/114764239
38 | INTER-TECH | 2019-10-07 | Modified | 113571141 | 1228944 | IMJ/2/S0394/2 | UG | Residential | Completed | Successful Installation
39 | INTER-TECH | 2019-10-07 | NewAcquisition | 115004349 | 1156338 | ITC/9/S7001/3 | B2H | Residential | Completed | Successful Installation
40 | INTER-TECH | 2019-10-07 | Modified | 114623997 | 1100542 | KTC/4/S0596/2 | B2H | Residential | Completed | Successful Installation
41 | INTER-TECH | 2019-10-07 | Modified | 115043115 | 77291 | KTC/4/S0562/10 | OH | Residential | Completed | Successful Installation | Old TR/113595530
42 | INTER-TECH | 2019-10-07 | Modified | 106712677 | 130045 | KBO/2/S0202/4 | B2H | Residential | Completed | Successful Installation
43 | INTER-TECH | 2019-10-07 | Modified | 114252611 | 1083735 | BIM/7/S0918/0 | B2H | Residential | Completed | Successful Installation
44 | INTER-TECH | 2019-10-07 | Modified | 114668668 | 1000268 | BIM/12/S1987/11 | B2H | Residential | Completed | Successful Installation
45 | INTER-TECH | 2019-10-07 | Modified | 114596037 | 1100873 | BIM/14/S2418/10 | B2H | Residential | Completed | Successful Installation
46 | INTER-TECH | 2019-10-07 | Modified | 114631287 | 1042967 | BIM/15/S2997/3 | B2H | Residential | Completed | Successful Installation
47 | INTER-TECH | 2019-10-07 | Modified | 114762038 | 1047357 | BIM/18/S3125/4 | B2H | Residential | Completed | Successful Installation
48 | INTER-TECH | 2019-10-07 | Modified | 114793708 | 161385 | KBO/4/S0442/2 | OH | Residential | Completed | Successful Installation
49 | INTER-TECH | 2019-10-07 | Modified | 114778966 | 1168307 | KBO/5/S0567/6 | B2H | Residential | Completed | Successful Installation
50 | INTER-TECH | 2019-10-07 | Modified | 114668752 | 28090 | KBO/6/S0642/1 | OH | Residential | Completed | Successful Installation
51 | INTER-TECH | 2019-10-07 | Modified | 114645571 | 1123531 | KBO/3/S0282/6 | UG | Residential | Completed | Successful Installation
52 | INTER-TECH | 2019-10-07 | Modified | 114230157 | 41038 | KBO/4/S0330/4 | OH | Residential | Completed | Successful Installation
53 | INTER-TECH | 2019-10-07 | Modified | 114877684 | 1203208 | KAL/3/S0448/12 | UG | Residential | Completed | Successful Installation
54 | INTER-TECH | 2019-10-07 | Modified | 113100095 | 1075510 | KTG/2/S0291/8 | UG | Residential | Completed | Successful Installation
55 | INTER-TECH | 2019-10-07 | Modified | 114664207 | 86694 | KRC/3/S0159/6 | UG | Residential | Completed | Successful Installation
56 | INTER-TECH | 2019-10-07 | Modified | 114666036 | 129076 | KRG/3/S0243/5 | UG | Residential | Completed | Successful Installation
57 | INTER-TECH | 2019-10-07 | Modified | 114272621 | 1245167 | KRG/7/S0954/0 | UG | Residential | Completed | Successful Installation
58 | INTER-TECH | 2019-10-07 | Modified | 115087518 | 171920 | KTG/2/S0211/8 | UG | Residential | Completed | Successful Installation | Old TR/114634049
59 | INTER-TECH | 2019-10-07 | Modified | 114746997 | 194051 | KTG/2/S0221/4 | UG | Residential | Completed | Successful Installation
60 | INTER-TECH | 2019-10-07 | Modified | 114880603 | 79886 | MSH/1/S0019 | UG | Residential | Completed | Successful Installation | Fibre Change Order
61 | INTER-TECH | 2019-10-07 | Modified | 114669258 | 62882 | KHX/1/S0095/1 | UG | Residential | Completed | Successful Installation
62 | INTER-TECH | 2019-10-07 | Modified | 114669198 | 1025548 | KHX/1/S0151/12 | UG | Residential | Completed | Successful Installation
63 | INTER-TECH | 2019-10-07 | Modified | 114669145 | 1188210 | KHX/2/S0303/15 | UG | Residential | Completed | Successful Installation
64 | INTER-TECH | 2019-10-07 | Modified | 114667396 | 1128294 | KHX/2/S0309/3 | UG | Residential | Completed | Successful Installation
65 | INTER-TECH | 2019-10-07 | Modified | 114669106 | 1134646 | KHX/2/S0318/0 | UG | Residential | Completed | Successful Installation
66 | INTER-TECH | 2019-10-07 | Modified | 114668956 | 35180 | KHX/6/S0612/13 | OH | Residential | Completed | Successful Installation
67 | INTER-TECH | 2019-10-07 | Modified | 115043616 | 79886 | MSH/1/S0019/13 | UG | Residential | Completed | Successful Installation | New UHD on Existing OTV
68 | INTER-TECH | 2019-10-07 | Modified | 114650292 | 18249 | ASJ/10/S0993/04 | UG | Residential | Completed | Successful Installation | ORBI HUB UPSELLING 12 MONTH
69 | INTER-TECH | 2019-10-07 | Modified | 114638866 | 68366 | DME/2/S0191/08 | UG | Residential | Completed | Successful Installation | ORBI HUB UPSELLING 24 MONTH
70 | INTER-TECH | 2019-10-07 | Modified | 114166548 | 50606 | DFS/1/S1557/03 | OH | Residential | Completed | Successful Installation | UHD TV UPSELLING
71 | INTER-TECH | 2019-10-07 | Copper | 109763567 | 118103 | IEK | UG | Business | Completed | Successful Installation
72 | INTER-TECH | 2019-10-07 | Modified | 112236342 | 1128107 | IEK | UG | Business | Completed | Successful Installation
73 | INTER-TECH | 2019-10-07 | Modified | 113971214 | 141674 |  | UG | Residential | Completed | Successful Installation | ADVANCED WIFI UPSELLING FOR 12 MONTHS
74 | INTER-TECH | 2019-10-07 | WLL | 114763470 |  | duhail |  | Residential | Completed | Successful Installation
75 | INTER-TECH | 2019-10-07 | Modified | 115089836 | 1112169 | KRG/1/S0077 | UG | Residential | Completed | Successful Installation | COMPLETED
76 | INTER-TECH | 2019-10-07 | NewAcquisition | 115016717 | 1273674 | USA/8/S1054/05 | UG | Residential | Completed | Successful Installation | COMPLETED
77 | INTER-TECH | 2019-10-07 | NewAcquisition | 113959979 | - | KRG/7/S0956 | B2H | Business | Completed | Successful Installation | COMPLETED
78 | INTER-TECH | 2019-10-07 | NewAcquisition | 114863464 | 1291558 | BIM/10/S4611 | B2H | Residential | Completed | Successful Installation | COMPLETED
79 | INTER-TECH | 2019-10-07 | NewAcquisition | 115040380 | 110146 | KBO/3/S0262/14 | B2H | Business | Completed | Successful Installation | COMPLETED
80 | INTER-TECH | 2019-10-07 | NewAcquisition | 113604596 | 1289846 | KHX/10/S1530 | UG | Residential | Completed | Successful Installation | COMPLETED
81 | INTER-TECH | 2019-10-07 | NewAcquisition | 111385922 | 1359101 | KHX/3/S0376 | UG | Business Residential | Completed | Successful Installation | COMPLETED
82 | INTER-TECH | 2019-10-07 | NewAcquisition | 114897291 | 1258375 | MSH/3/S0411 | B2H | Residential | Completed | Successful Installation | COMPLETED
83 | INTER-TECH | 2019-10-07 | Modified | 114669056 | 1051881 | KHX/5/S0527 | UG | Residential | Completed | Successful Installation | COMPLETED
84 | INTER-TECH | 2019-10-07 | Modified | 115041075 | 1034680 | KRN/1/S0114 | UG | Residential | Completed | Successful Installation | COMPLETED
85 | INTER-TECH | 2019-10-07 | NewAcquisition | 114765703 | 1297307 | KRN/4/S0496 | UG | Residential | Completed | Successful Installation | COMPLETED
86 | INTER-TECH | 2019-10-07 | NewAcquisition | 114657605 | 1252819 | LSL/17/S2829 | B2H | Residential | Completed | Successful Installation | COMPLETED
87 | INTER-TECH | 2019-10-07 | NewAcquisition | 114847291 | 1217830 | KAM/3/S0334 | UG | Residential | Completed | Successful Installation | COMPLETED
88 | INTER-TECH | 2019-10-07 | NewAcquisition | 113514864 | 1254929 | KTC/12/S1459 | B2H | Business | Completed | Successful Installation | COMPLETED
89 | INTER-TECH | 2019-10-07 | NewAcquisition | 114798534 | 1280241 | KTC/8/S1426 | B2H | Residential | Completed | Successful Installation | COMPLETED
90 | INTER-TECH | 2019-10-07 | migration | 114809042 | 26402 | KBO/10/S1542/15 | OH | Residential | Completed | Successful Installation | COMPLETED
91 | INTER-TECH | 2019-10-07 | NewAcquisition | 115090477 |  | BIM/15/S2574 | B2H | Residential | Completed | Successful Installation | COMPLETED
92 | INTER-TECH | 2019-10-07 | NewAcquisition | 114899319 | 1282723 | KAR/3/S0406/01 | UG | Residential | Completed | Successful Installation | COMPLETED
93 | INTER-TECH | 2019-10-07 | Modified | 115039189 | 1051946 | KTG/4/S0450 | UG | Residential | Completed | Successful Installation | COMPLETED
94 | INTER-TECH | 2019-10-07 | NewAcquisition | 114882813 | 1348477 | USM/3/S1808 | UG | Residential | Completed | Successful Installation | COMPLETED
95 | INTER-TECH | 2019-10-07 | NewAcquisition | 114809981 | 1067566 | USM/3/S0263 | UG | Residential | Completed | Successful Installation | COMPLETED
96 | INTER-TECH | 2019-10-07 | NewAcquisition | 114890474 | 1349187 | USM/5/S1542 | UG | Residential | Completed | Successful Installation | COMPLETED
97 | INTER-TECH | 2019-10-07 | NewAcquisition | 115095167 | 1184966 | WNG/1/S0197/05 | UG | Residential | Completed | Successful Installation | COMPLETED
98 | INTER-TECH | 2019-10-07 | NewAcquisition | 115090077 | 1363540 | KSM/2/S0327/13 | UG | Residential | Completed | Successful Installation | COMPLETED
99 | INTER-TECH | 2019-10-07 | NewAcquisition | 115106258 | 1184966 | WNG/1/S0197 | UG | Residential | Completed | Successful Installation | FIBER CHANGE ORDER
100 | INTER-TECH | 2019-10-07 | Modified | 114656209 | 41252 | KBO/1/S0113/3 | B2H | Residential | Pending | FTTX – Wrong Electricity Number | Correct SED 1228657 has an ONTSN: 48575443B3931495 with active DN 44340509 at customer premise. As per 118, no need to update comment from ISP side.
101 | INTER-TECH | 2019-10-07 | NewAcquisition | 114827931 | 1129906 | WBC/1/S0320 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE Ooredoo | PT MH burreid under construction
102 | INTER-TECH | 2019-10-07 | NewAcquisition | 114873687 | 165622 | WNG/2/S0147 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE Ooredoo | ODP to spliter manhole 2 mtr blockage under tile
103 | INTER-TECH | 2019-10-07 | migration | 115087752 | 105018 | AMQ/2/S0290 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE Ooredoo | Closure not having cable entry materials [ spacer,gormet ] informed quality Mr. Prem. He advised stop the work
104 | INTER-TECH | 2019-10-07 | Modified | 113987898 | 1202997 | WMR/2/S0270/5 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE Ooredoo | SMH to IDP blockage in 98mtr under interlock, pass to the internal civil team to clear and we will attend once the issue cleared
105 | INTER-TECH | 2019-10-07 | NewAcquisition | 114765643 | 1363544 | USA/7/S0948 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | IDP to ODP blocakge 1mtr and ODP to IDP blocakge 4 mtr under tile [ New qatari house customer will clear after few days ]
106 | INTER-TECH | 2019-10-07 | Migration | 87927518 | 122062 | NJC/4/S0488/14 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | IDP to zero MH blockage in 1mtr under tiles. As per customer, there is one MH available inside the customer premise. He will clear and call back us for installation
107 | INTER-TECH | 2019-10-07 | NewAcquisition | 114995461 | 15868 | NJC/7/S5355/4 | OH | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | Car parked over two PMH
108 | INTER-TECH | 2019-10-07 | NewAcquisition | 113985578 | 1085093 | AAT/3/S0452/4 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | Car parked over SMH
109 | INTER-TECH | 2019-10-07 | NewAcquisition | 108269027 | 25505 | BIM/15/S2510 | UG | Business | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | MANHOLE COVERED BY CAR
110 | INTER-TECH | 2019-10-07 | migration | 93359368 | 107848 | KTG/2/S0238 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | IDP TO MANHOLE 1M BLOCKEGE, UNDER TILE INSIDE THE VILLA
111 | INTER-TECH | 2019-10-07 | NewAcquisition | 99783479 | 154750 | IEC/3/S0412 | UG | Residential | Pending | FTTX - Splitter not installed | G+2 building G flor 30 shop 1st flor 37 room 2nd flor 11 room all have SED available FAT not installed still now
112 | INTER-TECH | 2019-10-07 | NewAcquisition | 106686476 | 1285241 | KAM/3/S0454 | UG | Business Residential | Pending | FTTX - Splitter not installed | NO POWER IN THIS SPLITTER
113 | INTER-TECH | 2019-10-07 | Modified | 115105337 | 1183677 | WKZ/4/S0501/4 | UG | Business | Pending | FTTX - Sharing Villa IDP Access issue | IDP room tenant not available[Old TR/114887069]
114 | INTER-TECH | 2019-10-07 | NewAcquisition | 114876993 | 1107488 | NJC/11/S1370/12 | B2H | Residential | Pending | FTTX - RE-MIGRATION | LO ONT SN: 485754435B1938B, LO ONT have active DN: 40383858. Pending with back office
115 | INTER-TECH | 2019-10-07 | migration | 99656259 | 1346240 | BIM/12/S4606 | B2H | Business | Pending | FTTX - Pending due to service activation issues | PENDING WITH BACK OFFICE
116 | INTER-TECH | 2019-10-07 | Modified | 115045982 | 1011116 | WBS/5/S0673 | B2H | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed Thursday morning
117 | INTER-TECH | 2019-10-07 | NewAcquisition | 98965937 | 1168784 | WBY/1/S0731 | UG | Business | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed wendesday 1pm
118 | INTER-TECH | 2019-10-07 | NewAcquisition | 114892532 | 1172877 | USA/4/S0415 | UG | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed tomorrow 4pm
119 | INTER-TECH | 2019-10-07 | NewAcquisition | 114896827 | 1265324 | MKD/2/S1212/9 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow afternoon, POC-70747321. As per customer, his house shifting is not yet completed.
120 | INTER-TECH | 2019-10-07 | Modified | 115043111 | 1248305 | WUK/15/S3020/4 |  | Business | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow after 03:00PM. As per customer, his appointment is tomorrow POC-50490090
121 | INTER-TECH | 2019-10-07 | Modified | 113912775 | 1077643 | MKD/3/S0314/5 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to 12-10-2019, POC-55791549
122 | INTER-TECH | 2019-10-07 | Modified | 113992532 | 105418 | DME/1/S2140/4 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow morning, POC-30781405
123 | INTER-TECH | 2019-10-07 | Migration | 111105573 | 70388 | IMA/1/S0036/4 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow morning 09:00AM, POC- 55547041
124 | INTER-TECH | 2019-10-07 | Modified | 114660838 | 1208392 | KMN/2/S0385/7 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow
125 | INTER-TECH | 2019-10-07 | NewAcquisition | 106407407 | Q-641949 | BIM/17/S2926/8 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to after one month
126 | INTER-TECH | 2019-10-07 | NewAcquisition | 114864811 | 1077058 | BIM/12/S1981 | B2H | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | CUSTOMER POSTPONED FOR OCT-09@7.00PM
127 | INTER-TECH | 2019-10-07 | NewAcquisition | 91372732 |  | BIM | B2H | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | CUSTOMER POSTPONED
128 | INTER-TECH | 2019-10-07 | Modified | 106528821 | 158908 | BIM/11/S1279 | B2H | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | Customer not reachable
129 | INTER-TECH | 2019-10-07 | Modified | 106774180 | 68900 | KBO/8/S1359/11 |  | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | Customer not answering call
130 | INTER-TECH | 2019-10-07 | Modified | 106563401 | 166186 | BIM/15/S4392/2 |  | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | Given contact number is wrong person
131 | INTER-TECH | 2019-10-07 | Modified | 115049702 | 1281289 | KSM/2/S0430/0 |  | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | Customer GSM off
132 | INTER-TECH | 2019-10-07 | migration | 90668696 | 155706 | KTC/10/S1305 | UG | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | CUSTOMER NO ANSWER
133 | INTER-TECH | 2019-10-07 | NewAcquisition | 87442134 | 173731 | KAM | UG | Residential | Pending | FTTX - Customer Cancelled/Not applied | Alread customer have fibar same del number
134 | INTER-TECH | 2019-10-07 | NewAcquisition | 114889902 | 1231738 | USA/10/S1159 | UG | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled [ First flor IDP room customer not allowed to pull cable asper our customer cancelled aplication]
135 | INTER-TECH | 2019-10-07 | NewAcquisition | 114242668 | 1006433 | RAS/15/S2223/10 |  | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled. As per customer, is already completed on 12 days before
136 | INTER-TECH | 2019-10-07 | Modified | 114664796 | 151767 | BIM/12/S2019/1 |  | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled
137 | INTER-TECH | 2019-10-07 | Modified | 114660519 | 1138690 | KHX/2/S0285/5 |  | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled
138 | INTER-TECH | 2019-10-07 | Modified | 114660451 | 1040550 | KHX/2/S0288/1 | UG | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled
139 | INTER-TECH | 2019-10-07 | NewAcquisition | 114895143 | 1102226 | KRC/4/S0314 | UG | Residential | Pending | FTTX - Customer Cancelled/Not applied | CUSTOMER CANCELLED

## New Acquisitions
SN | Supplier Name | Appointment Date | Type | WO No. | Electricity No. | Site ID | Installation Scenario | Segment | Remarks | Description | Additional Description
1 | INTER-TECH | 2019-10-07 | NewAcquisition | 114842431 | 1285777 | LSL/17/S2841 | B2H | Residential | Completed | Successful Installation
2 | INTER-TECH | 2019-10-07 | NewAcquisition | 114871916 | 149123 | WBK/1/S0056 | UG | Business | Completed | Successful Installation
3 | INTER-TECH | 2019-10-07 | NewAcquisition | 112246798 | 1291196 | LSL/16/S3006 | B2H | Business | Completed | Successful Installation
4 | INTER-TECH | 2019-10-07 | NewAcquisition | 113328984 | 1258047 | USA/8/S1056 | UG | Residential | Completed | Successful Installation
5 | INTER-TECH | 2019-10-07 | NewAcquisition | 115004532 | 147462 | MKD/4/S0858 | UG | Residential | Completed | Successful Installation
6 | INTER-TECH | 2019-10-07 | NewAcquisition | 114761537 | 1285758 | LSL/17/S2839 | B2H | Residential | Completed | Successful Installation
7 | INTER-TECH | 2019-10-07 | NewAcquisition | 114776246 | 1357812 | KAE/1/S0010 | UG | Residential | Completed | Successful Installation
8 | INTER-TECH | 2019-10-07 | NewAcquisition | 106039346 | 1355978 | USM/6/S1073 | UG | Residential | Completed | Successful Installation
9 | INTER-TECH | 2019-10-07 | NewAcquisition | 114604609 | 1002340 | WBS/2/S0203 | B2H | Residential | Completed | Successful Installation
10 | INTER-TECH | 2019-10-07 | NewAcquisition | 114245418 | - | WBS/4/S1272 | B2H | Business Residential | Completed | Successful Installation
11 | INTER-TECH | 2019-10-07 | NewAcquisition | 115077466 | 1208568 | KRC/4/S0449 | UG | Residential | Completed | Successful Installation
12 | INTER-TECH | 2019-10-07 | NewAcquisition | 113275008 | 1246587 | WBL/3/S0169 | UG | Residential | Completed | Successful Installation
13 | INTER-TECH | 2019-10-07 | NewAcquisition | 113526410 | 1208568 | KRC/4/S0449 | UG | Residential | Completed | Successful Installation
14 | INTER-TECH | 2019-10-07 | NewAcquisition | 115058017 | 1357374 | KSM/2/S0329 | UG | Residential | Completed | Successful Installation
15 | INTER-TECH | 2019-10-07 | NewAcquisition | 114223324 | 123572 | RAS/6/S0764/4 | B2H | Residential | Completed | Successful Installation
16 | INTER-TECH | 2019-10-07 | NewAcquisition | 114243618 | 1248318 | WUK/15/S3021/5 | B2H | Residential | Completed | Successful Installation
17 | INTER-TECH | 2019-10-07 | NewAcquisition | 115060213 | 1141911 | WUK/1/S0424/1 | UG | Residential | Completed | Successful Installation | Old TR/115000704
18 | INTER-TECH | 2019-10-07 | NewAcquisition | 115087188 | 148250 | MKD/2/S0818/12 | UG | Residential | Completed | Successful Installation | Old TR/114851539
19 | INTER-TECH | 2019-10-07 | NewAcquisition | 115106620 | 157412 | IAK/1/S0422/8 | B2H | Residential | Completed | Successful Installation | Old TR/114764239
20 | INTER-TECH | 2019-10-07 | NewAcquisition | 115004349 | 1156338 | ITC/9/S7001/3 | B2H | Residential | Completed | Successful Installation
21 | INTER-TECH | 2019-10-07 | NewAcquisition | 115016717 | 1273674 | USA/8/S1054/05 | UG | Residential | Completed | Successful Installation | COMPLETED
22 | INTER-TECH | 2019-10-07 | NewAcquisition | 113959979 | - | KRG/7/S0956 | B2H | Business | Completed | Successful Installation | COMPLETED
23 | INTER-TECH | 2019-10-07 | NewAcquisition | 114863464 | 1291558 | BIM/10/S4611 | B2H | Residential | Completed | Successful Installation | COMPLETED
24 | INTER-TECH | 2019-10-07 | NewAcquisition | 115040380 | 110146 | KBO/3/S0262/14 | B2H | Business | Completed | Successful Installation | COMPLETED
25 | INTER-TECH | 2019-10-07 | NewAcquisition | 113604596 | 1289846 | KHX/10/S1530 | UG | Residential | Completed | Successful Installation | COMPLETED
26 | INTER-TECH | 2019-10-07 | NewAcquisition | 111385922 | 1359101 | KHX/3/S0376 | UG | Business Residential | Completed | Successful Installation | COMPLETED
27 | INTER-TECH | 2019-10-07 | NewAcquisition | 114897291 | 1258375 | MSH/3/S0411 | B2H | Residential | Completed | Successful Installation | COMPLETED
28 | INTER-TECH | 2019-10-07 | NewAcquisition | 114765703 | 1297307 | KRN/4/S0496 | UG | Residential | Completed | Successful Installation | COMPLETED
29 | INTER-TECH | 2019-10-07 | NewAcquisition | 114657605 | 1252819 | LSL/17/S2829 | B2H | Residential | Completed | Successful Installation | COMPLETED
30 | INTER-TECH | 2019-10-07 | NewAcquisition | 114847291 | 1217830 | KAM/3/S0334 | UG | Residential | Completed | Successful Installation | COMPLETED
31 | INTER-TECH | 2019-10-07 | NewAcquisition | 113514864 | 1254929 | KTC/12/S1459 | B2H | Business | Completed | Successful Installation | COMPLETED
32 | INTER-TECH | 2019-10-07 | NewAcquisition | 114798534 | 1280241 | KTC/8/S1426 | B2H | Residential | Completed | Successful Installation | COMPLETED
33 | INTER-TECH | 2019-10-07 | NewAcquisition | 115090477 |  | BIM/15/S2574 | B2H | Residential | Completed | Successful Installation | COMPLETED
34 | INTER-TECH | 2019-10-07 | NewAcquisition | 114899319 | 1282723 | KAR/3/S0406/01 | UG | Residential | Completed | Successful Installation | COMPLETED
35 | INTER-TECH | 2019-10-07 | NewAcquisition | 114882813 | 1348477 | USM/3/S1808 | UG | Residential | Completed | Successful Installation | COMPLETED
36 | INTER-TECH | 2019-10-07 | NewAcquisition | 114809981 | 1067566 | USM/3/S0263 | UG | Residential | Completed | Successful Installation | COMPLETED
37 | INTER-TECH | 2019-10-07 | NewAcquisition | 114890474 | 1349187 | USM/5/S1542 | UG | Residential | Completed | Successful Installation | COMPLETED
38 | INTER-TECH | 2019-10-07 | NewAcquisition | 115095167 | 1184966 | WNG/1/S0197/05 | UG | Residential | Completed | Successful Installation | COMPLETED
39 | INTER-TECH | 2019-10-07 | NewAcquisition | 115090077 | 1363540 | KSM/2/S0327/13 | UG | Residential | Completed | Successful Installation | COMPLETED
40 | INTER-TECH | 2019-10-07 | NewAcquisition | 115106258 | 1184966 | WNG/1/S0197 | UG | Residential | Completed | Successful Installation | FIBER CHANGE ORDER
41 | INTER-TECH | 2019-10-07 | NewAcquisition | 114827931 | 1129906 | WBC/1/S0320 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE Ooredoo | PT MH burreid under construction
42 | INTER-TECH | 2019-10-07 | NewAcquisition | 114873687 | 165622 | WNG/2/S0147 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE Ooredoo | ODP to spliter manhole 2 mtr blockage under tile
43 | INTER-TECH | 2019-10-07 | NewAcquisition | 114765643 | 1363544 | USA/7/S0948 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | IDP to ODP blocakge 1mtr and ODP to IDP blocakge 4 mtr under tile [ New qatari house customer will clear after few days ]
44 | INTER-TECH | 2019-10-07 | NewAcquisition | 114995461 | 15868 | NJC/7/S5355/4 | OH | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | Car parked over two PMH
45 | INTER-TECH | 2019-10-07 | NewAcquisition | 113985578 | 1085093 | AAT/3/S0452/4 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | Car parked over SMH
46 | INTER-TECH | 2019-10-07 | NewAcquisition | 108269027 | 25505 | BIM/15/S2510 | UG | Business | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | MANHOLE COVERED BY CAR
47 | INTER-TECH | 2019-10-07 | NewAcquisition | 99783479 | 154750 | IEC/3/S0412 | UG | Residential | Pending | FTTX - Splitter not installed | G+2 building G flor 30 shop 1st flor 37 room 2nd flor 11 room all have SED available FAT not installed still now
48 | INTER-TECH | 2019-10-07 | NewAcquisition | 106686476 | 1285241 | KAM/3/S0454 | UG | Business Residential | Pending | FTTX - Splitter not installed | NO POWER IN THIS SPLITTER
49 | INTER-TECH | 2019-10-07 | NewAcquisition | 114876993 | 1107488 | NJC/11/S1370/12 | B2H | Residential | Pending | FTTX - RE-MIGRATION | LO ONT SN: 485754435B1938B, LO ONT have active DN: 40383858. Pending with back office
50 | INTER-TECH | 2019-10-07 | NewAcquisition | 98965937 | 1168784 | WBY/1/S0731 | UG | Business | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed wendesday 1pm
51 | INTER-TECH | 2019-10-07 | NewAcquisition | 114892532 | 1172877 | USA/4/S0415 | UG | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed tomorrow 4pm
52 | INTER-TECH | 2019-10-07 | NewAcquisition | 114896827 | 1265324 | MKD/2/S1212/9 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow afternoon, POC-70747321. As per customer, his house shifting is not yet completed.
53 | INTER-TECH | 2019-10-07 | NewAcquisition | 106407407 | Q-641949 | BIM/17/S2926/8 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to after one month
54 | INTER-TECH | 2019-10-07 | NewAcquisition | 114864811 | 1077058 | BIM/12/S1981 | B2H | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | CUSTOMER POSTPONED FOR OCT-09@7.00PM
55 | INTER-TECH | 2019-10-07 | NewAcquisition | 91372732 |  | BIM | B2H | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | CUSTOMER POSTPONED
56 | INTER-TECH | 2019-10-07 | NewAcquisition | 87442134 | 173731 | KAM | UG | Residential | Pending | FTTX - Customer Cancelled/Not applied | Alread customer have fibar same del number
57 | INTER-TECH | 2019-10-07 | NewAcquisition | 114889902 | 1231738 | USA/10/S1159 | UG | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled [ First flor IDP room customer not allowed to pull cable asper our customer cancelled aplication]
58 | INTER-TECH | 2019-10-07 | NewAcquisition | 114242668 | 1006433 | RAS/15/S2223/10 |  | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled. As per customer, is already completed on 12 days before
59 | INTER-TECH | 2019-10-07 | NewAcquisition | 114895143 | 1102226 | KRC/4/S0314 | UG | Residential | Pending | FTTX - Customer Cancelled/Not applied | CUSTOMER CANCELLED

## Migration
SN | Supplier Name | Appointment Date | Type | WO No. | Electricity No. | Site ID | Installation Scenario | Segment | Remarks | Description | Additional Description
1 | INTER-TECH | 2019-10-07 | migration | 94752562 | 125113 | WBY/1/S0023 | UG | Residential | Completed | Successful Installation
2 | INTER-TECH | 2019-10-07 | migration | 114243742 | 72593 | WBC/1/S0357 | UG | Residential | Completed | Successful Installation
3 | INTER-TECH | 2019-10-07 | migration | 113261535 | 102093 | NJC-20-M254-1 | MDU | Residential | Completed | Successful Installation
4 | INTER-TECH | 2019-10-07 | migration | 114809042 | 26402 | KBO/10/S1542/15 | OH | Residential | Completed | Successful Installation | COMPLETED
5 | INTER-TECH | 2019-10-07 | migration | 115087752 | 105018 | AMQ/2/S0290 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE Ooredoo | Closure not having cable entry materials [ spacer,gormet ] informed quality Mr. Prem. He advised stop the work
6 | INTER-TECH | 2019-10-07 | Migration | 87927518 | 122062 | NJC/4/S0488/14 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | IDP to zero MH blockage in 1mtr under tiles. As per customer, there is one MH available inside the customer premise. He will clear and call back us for installation
7 | INTER-TECH | 2019-10-07 | migration | 93359368 | 107848 | KTG/2/S0238 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE - CUSTOMER SIDE | IDP TO MANHOLE 1M BLOCKEGE, UNDER TILE INSIDE THE VILLA
8 | INTER-TECH | 2019-10-07 | migration | 99656259 | 1346240 | BIM/12/S4606 | B2H | Business | Pending | FTTX - Pending due to service activation issues | PENDING WITH BACK OFFICE
9 | INTER-TECH | 2019-10-07 | Migration | 111105573 | 70388 | IMA/1/S0036/4 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow morning 09:00AM, POC- 55547041
10 | INTER-TECH | 2019-10-07 | migration | 90668696 | 155706 | KTC/10/S1305 | UG | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | CUSTOMER NO ANSWER

## CPE-MODIFIED
SN | Supplier Name | Appointment Date | Type | WO No. | Electricity No. | Site ID | Installation Scenario | Segment | Remarks | Description | Additional Description
1 | INTER-TECH | 2019-10-07 | Modified | 113569087 | 1041994 | BIM/8/S1503 | B2H | Residential | Completed | Successful Installation
2 | INTER-TECH | 2019-10-07 | Modified | 114752500 | - | BIM/11/S1287 | B2H | Business Residential | Completed | Successful Installation
3 | INTER-TECH | 2019-10-07 | Modified | 114660927 | 198478 | BIM/18/S4508 | B2H | Residential | Completed | Successful Installation
4 | INTER-TECH | 2019-10-07 | Modified | 115068075 | 1100896 | BIM/14/S2423 | B2H | Residential | Completed | Successful Installation
5 | INTER-TECH | 2019-10-07 | Modified | 115091103 | 130841 | BIM/2/S2399 | B2H | Residential | Completed | Successful Installation
6 | INTER-TECH | 2019-10-07 | Modified | 114170207 | 1017099 | BIM/6/S0636 | B2H | Residential | Completed | Successful Installation
7 | INTER-TECH | 2019-10-07 | Modified | 115041362 | 1156097 | KRC/4/S0359 | UG | Residential | Completed | Successful Installation
8 | INTER-TECH | 2019-10-07 | Modified | 115103531 | 88226 | DFS/6/S1607 | B2H | Business | Completed | Successful Installation
9 | INTER-TECH | 2019-10-07 | Modified | 115107789 | 45362 | KMN/1/S0075 | OH | Residential | Completed | Successful Installation | OLD TID : 114663620
10 | INTER-TECH | 2019-10-07 | Modified | 115105388 | 130799 | BIM/2/S4397 | B2H | Business | Completed | Successful Installation
11 | INTER-TECH | 2019-10-07 | Modified | 114890792 | 1140298 | DME/8/S1288/0 | B2H | Residential | Completed | Successful Installation
12 | INTER-TECH | 2019-10-07 | Modified | 115094998 | 1344267 | WUK/11/S1627/7 | UG | Residential | Completed | Successful Installation | Old TR/113596130
13 | INTER-TECH | 2019-10-07 | Modified | 115051420 | Q-120788 | MKD/6/S0799/12 | B2H | Residential | Completed | Successful Installation | Old TR/114240949
14 | INTER-TECH | 2019-10-07 | Modified | 115092322 | 12018 | NJC/17/S2182/13 | OH | Residential | Completed | Successful Installation | Old TR/114997999
15 | INTER-TECH | 2019-10-07 | Modified | 112852739 | 1130251 | IME/4/S0421/1 | UG | Residential | Completed | Successful Installation
16 | INTER-TECH | 2019-10-07 | Modified | 113571141 | 1228944 | IMJ/2/S0394/2 | UG | Residential | Completed | Successful Installation
17 | INTER-TECH | 2019-10-07 | Modified | 114623997 | 1100542 | KTC/4/S0596/2 | B2H | Residential | Completed | Successful Installation
18 | INTER-TECH | 2019-10-07 | Modified | 115043115 | 77291 | KTC/4/S0562/10 | OH | Residential | Completed | Successful Installation | Old TR/113595530
19 | INTER-TECH | 2019-10-07 | Modified | 106712677 | 130045 | KBO/2/S0202/4 | B2H | Residential | Completed | Successful Installation
20 | INTER-TECH | 2019-10-07 | Modified | 114252611 | 1083735 | BIM/7/S0918/0 | B2H | Residential | Completed | Successful Installation
21 | INTER-TECH | 2019-10-07 | Modified | 114668668 | 1000268 | BIM/12/S1987/11 | B2H | Residential | Completed | Successful Installation
22 | INTER-TECH | 2019-10-07 | Modified | 114596037 | 1100873 | BIM/14/S2418/10 | B2H | Residential | Completed | Successful Installation
23 | INTER-TECH | 2019-10-07 | Modified | 114631287 | 1042967 | BIM/15/S2997/3 | B2H | Residential | Completed | Successful Installation
24 | INTER-TECH | 2019-10-07 | Modified | 114762038 | 1047357 | BIM/18/S3125/4 | B2H | Residential | Completed | Successful Installation
25 | INTER-TECH | 2019-10-07 | Modified | 114793708 | 161385 | KBO/4/S0442/2 | OH | Residential | Completed | Successful Installation
26 | INTER-TECH | 2019-10-07 | Modified | 114778966 | 1168307 | KBO/5/S0567/6 | B2H | Residential | Completed | Successful Installation
27 | INTER-TECH | 2019-10-07 | Modified | 114668752 | 28090 | KBO/6/S0642/1 | OH | Residential | Completed | Successful Installation
28 | INTER-TECH | 2019-10-07 | Modified | 114645571 | 1123531 | KBO/3/S0282/6 | UG | Residential | Completed | Successful Installation
29 | INTER-TECH | 2019-10-07 | Modified | 114230157 | 41038 | KBO/4/S0330/4 | OH | Residential | Completed | Successful Installation
30 | INTER-TECH | 2019-10-07 | Modified | 114877684 | 1203208 | KAL/3/S0448/12 | UG | Residential | Completed | Successful Installation
31 | INTER-TECH | 2019-10-07 | Modified | 113100095 | 1075510 | KTG/2/S0291/8 | UG | Residential | Completed | Successful Installation
32 | INTER-TECH | 2019-10-07 | Modified | 114664207 | 86694 | KRC/3/S0159/6 | UG | Residential | Completed | Successful Installation
33 | INTER-TECH | 2019-10-07 | Modified | 114666036 | 129076 | KRG/3/S0243/5 | UG | Residential | Completed | Successful Installation
34 | INTER-TECH | 2019-10-07 | Modified | 114272621 | 1245167 | KRG/7/S0954/0 | UG | Residential | Completed | Successful Installation
35 | INTER-TECH | 2019-10-07 | Modified | 115087518 | 171920 | KTG/2/S0211/8 | UG | Residential | Completed | Successful Installation | Old TR/114634049
36 | INTER-TECH | 2019-10-07 | Modified | 114746997 | 194051 | KTG/2/S0221/4 | UG | Residential | Completed | Successful Installation
37 | INTER-TECH | 2019-10-07 | Modified | 114880603 | 79886 | MSH/1/S0019 | UG | Residential | Completed | Successful Installation | Fibre Change Order
38 | INTER-TECH | 2019-10-07 | Modified | 114669258 | 62882 | KHX/1/S0095/1 | UG | Residential | Completed | Successful Installation
39 | INTER-TECH | 2019-10-07 | Modified | 114669198 | 1025548 | KHX/1/S0151/12 | UG | Residential | Completed | Successful Installation
40 | INTER-TECH | 2019-10-07 | Modified | 114669145 | 1188210 | KHX/2/S0303/15 | UG | Residential | Completed | Successful Installation
41 | INTER-TECH | 2019-10-07 | Modified | 114667396 | 1128294 | KHX/2/S0309/3 | UG | Residential | Completed | Successful Installation
42 | INTER-TECH | 2019-10-07 | Modified | 114669106 | 1134646 | KHX/2/S0318/0 | UG | Residential | Completed | Successful Installation
43 | INTER-TECH | 2019-10-07 | Modified | 114668956 | 35180 | KHX/6/S0612/13 | OH | Residential | Completed | Successful Installation
44 | INTER-TECH | 2019-10-07 | Modified | 115043616 | 79886 | MSH/1/S0019/13 | UG | Residential | Completed | Successful Installation | New UHD on Existing OTV
45 | INTER-TECH | 2019-10-07 | Modified | 114650292 | 18249 | ASJ/10/S0993/04 | UG | Residential | Completed | Successful Installation | ORBI HUB UPSELLING 12 MONTH
46 | INTER-TECH | 2019-10-07 | Modified | 114638866 | 68366 | DME/2/S0191/08 | UG | Residential | Completed | Successful Installation | ORBI HUB UPSELLING 24 MONTH
47 | INTER-TECH | 2019-10-07 | Modified | 114166548 | 50606 | DFS/1/S1557/03 | OH | Residential | Completed | Successful Installation | UHD TV UPSELLING
48 | INTER-TECH | 2019-10-07 | Modified | 112236342 | 1128107 | IEK | UG | Business | Completed | Successful Installation
49 | INTER-TECH | 2019-10-07 | Modified | 113971214 | 141674 |  | UG | Residential | Completed | Successful Installation | ADVANCED WIFI UPSELLING FOR 12 MONTHS
50 | INTER-TECH | 2019-10-07 | Modified | 115089836 | 1112169 | KRG/1/S0077 | UG | Residential | Completed | Successful Installation | COMPLETED
51 | INTER-TECH | 2019-10-07 | Modified | 114669056 | 1051881 | KHX/5/S0527 | UG | Residential | Completed | Successful Installation | COMPLETED
52 | INTER-TECH | 2019-10-07 | Modified | 115041075 | 1034680 | KRN/1/S0114 | UG | Residential | Completed | Successful Installation | COMPLETED
53 | INTER-TECH | 2019-10-07 | Modified | 115039189 | 1051946 | KTG/4/S0450 | UG | Residential | Completed | Successful Installation | COMPLETED
54 | INTER-TECH | 2019-10-07 | Modified | 114656209 | 41252 | KBO/1/S0113/3 | B2H | Residential | Pending | FTTX – Wrong Electricity Number | Correct SED 1228657 has an ONTSN: 48575443B3931495 with active DN 44340509 at customer premise. As per 118, no need to update comment from ISP side.
55 | INTER-TECH | 2019-10-07 | Modified | 113987898 | 1202997 | WMR/2/S0270/5 | UG | Residential | Pending | FTTX - TECHNICAL ISSUE Ooredoo | SMH to IDP blockage in 98mtr under interlock, pass to the internal civil team to clear and we will attend once the issue cleared
56 | INTER-TECH | 2019-10-07 | Modified | 115105337 | 1183677 | WKZ/4/S0501/4 | UG | Business | Pending | FTTX - Sharing Villa IDP Access issue | IDP room tenant not available[Old TR/114887069]
57 | INTER-TECH | 2019-10-07 | Modified | 115045982 | 1011116 | WBS/5/S0673 | B2H | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed Thursday morning
58 | INTER-TECH | 2019-10-07 | Modified | 115043111 | 1248305 | WUK/15/S3020/4 |  | Business | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow after 03:00PM. As per customer, his appointment is tomorrow POC-50490090
59 | INTER-TECH | 2019-10-07 | Modified | 113912775 | 1077643 | MKD/3/S0314/5 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to 12-10-2019, POC-55791549
60 | INTER-TECH | 2019-10-07 | Modified | 113992532 | 105418 | DME/1/S2140/4 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow morning, POC-30781405
61 | INTER-TECH | 2019-10-07 | Modified | 114660838 | 1208392 | KMN/2/S0385/7 |  | Residential | Pending | FTTX - CUSTOMER POSTPONED INSTALLATION | Customer postponed to tomorrow
62 | INTER-TECH | 2019-10-07 | Modified | 106528821 | 158908 | BIM/11/S1279 | B2H | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | Customer not reachable
63 | INTER-TECH | 2019-10-07 | Modified | 106774180 | 68900 | KBO/8/S1359/11 |  | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | Customer not answering call
64 | INTER-TECH | 2019-10-07 | Modified | 106563401 | 166186 | BIM/15/S4392/2 |  | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | Given contact number is wrong person
65 | INTER-TECH | 2019-10-07 | Modified | 115049702 | 1281289 | KSM/2/S0430/0 |  | Residential | Pending | FTTX - CUSTOMER NOT REACHABLE | Customer GSM off
66 | INTER-TECH | 2019-10-07 | Modified | 114664796 | 151767 | BIM/12/S2019/1 |  | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled
67 | INTER-TECH | 2019-10-07 | Modified | 114660519 | 1138690 | KHX/2/S0285/5 |  | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled
68 | INTER-TECH | 2019-10-07 | Modified | 114660451 | 1040550 | KHX/2/S0288/1 | UG | Residential | Pending | FTTX - Customer Cancelled/Not applied | Customer cancelled

## Sheet10 (hidden)
151 | INTERTECH | 2017-05-20 | New Acquisition | 56927902 | 1202505 | DNJ/1/S0564/9 | UG | Residential | Pending | Fttx-Customer cancelled-Not applied | Customer cancelled | TENIN | 44216034
152 | INTERTECH | 2017-05-20 | New Acquisition | 57031568 | 1219470 | WKA/2/S1042/6 | B2H | Business | Pending | Fttx-Customer cancelled-Not applied | Customer cancelled (He got service two week before | SAFWAN | 40397166
153 | INTERTECH | 2017-05-20 | New Acquisition | 100414680 | 135693 | IAK/1/S0381/13 | UG | Business Residential | Pending | Fttx-Customer cancelled-Not applied | Customer no need fibar conection | NARESH | 44580980
154 | INTERTECH | 2017-05-20 | New Acquisition | 56559372 | 58502 | DME/2/S2332/3 | UG | Residential | Pending | Fttx-Customer cancelled-Not applied | CUSTOMER CANCELLED | MUSTAFA | 44659930
155 | INTERTECH | 2017-05-20 | New Acquisition | 57307686 | 1014755 | APC/1/S0003/2 | UG | Residential | Pending | Fttx-Customer cancelled-Not applied | CUSTOMER CANCELLED | NAWAS | 44415246
156 | INTERTECH | 2017-05-20 | New Acquisition | 54722932 | 1201362 | IMJ/2/S0181/5 | UG | Residential | Pending | Fttx-Customer cancelled-Not applied | CUSTOMER CANCELLED | HASEEB | 44432741
157 | INTERTECH | 2017-05-20 | New Acquisition | 57029977 | 573311 | RAS/5/S0634/6 | B2H | Business Residential | Pending | Fttx-Customer cancelled-Not applied | CUSTOMER CANCELLED | PRASANTH.S | 44630689
158 | INTERTECH | 2017-05-20 | New Acquisition | 55251804 | 1132515 | WUK/1/S0039/7 | UG | Residential | Pending | Fttx-Customer cancelled-Not applied | Customer cancelled | SULAIMAN | 44410143
159 | INTERTECH | 2017-05-20 | New Acquisition | 56890634 | 1203875 | WUK/1/S0128/7 | UG | Residential | Pending | Fttx-Customer cancelled-Not applied | Customer cancelled | SULAIMAN | 44694238